## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | High satisfaction with the checkout process. | 82% of participants agreed that the checkout process was quick, easy, and secure. | Continue optimizing the checkout process and ensure user-friendliness in future rollouts.
Customers | Went well | Guests enjoyed the tablet experience overall. | 40% rated the experience as "great," and 40% preferred the tablet system over waiter-only service. | Build on this preference and enhance the tablet's features to solidify customer satisfaction.
Customers | Needs improvement | Table wait times were longer than expected. | 54% of customers reported waiting more than 15 minutes for a table. | Implement strategies to reduce table turn time, such as improving tablet usage efficiency.
Customers | Needs improvement | Order accuracy could be improved. | 28% of customers reported incorrect orders. | Address kitchen-to-tablet integration issues to reduce errors.
Customers | Needs improvement | Some technical glitches with tablets. | 12% of participants reported technical issues, such as freezing screens. | Increase technical support during rollouts and improve system reliability.
Project team | Went well | Successful tablet installation at both locations. | Feedback from Alex and Gilly during the meeting. | Use the installation process as a model for future locations.
Project team | Went well | Weekly vendor calls improved coordination. | Peta mentioned that these calls clarified task dependencies. | Maintain weekly calls during future rollouts to ensure alignment.
Project team | Needs improvement | Table turn time did not improve as expected. | Both Alex and Gilly reported minimal improvement in table turn times. | Analyze tablet workflows and train staff to better optimize time management.
Project team | Needs improvement | Operational inefficiencies impacted task execution. | Peta noted internal operational issues as a challenge. | Conduct pre-rollout assessments to address location-specific operational challenges in advance.
Project team | Needs improvement | Lack of comprehensive staff training. | Alex suggested splitting training into two parts for better effectiveness. | Revise the training process to focus on both tablet usage and overall service operations.